## Project Timeline
PantryRaid
PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2017-09-01 | Project Start | 25 | 0 | 25 | 2017-09-01 | Project Start
2017-09-25 | Vision Document | 5 | 0 | 5 | 2017-09-25 | Vision Document
2017-10-02 | Project Plan | -10 | 0 | -10 | 2017-10-02 | Project Plan
2017-10-16 | Flowchart/UML | 15 | 0 | 15 | 2017-10-16 | Flowchart/UML
2017-11-06 | Use Cases | -15 | 0 | -15 | 2017-11-06 | Use Cases
2017-11-29 | Test Plan | 10 | 0 | 10 | 2017-11-29 | Test Plan
2017-12-02 | User Manual Draft (Tentative) | -15 | 0 | -15 | 2017-12-02 | User Manual Draft (Tentative)
2017-12-19 | Presentation | 15 | 0 | 15 | 2017-12-19 | Presentation
2018-01-29 | Implementation Phase | -25 | 0 | -25 | 2018-01-29 | Implementation Phase
2018-02-14 | Dababase Implementation | 15 | 0 | -12 | 2018-02-14 | User Interface: "Layout"
2018-02-14 | User Interface: "Layout" | -12 | 0 | 15 | 2018-02-14 | Dababase Implementation
2018-03-21 | User Interface: "Validation" | 25 | 0 | -30 | 2018-03-20 | Prototype Testing
2018-03-20 | Prototype Testing | -30 | 0 | 5 | 2018-03-21 | Prototype Finished
2018-03-21 | Prototype Finished | 5 | 0 | 25 | 2018-03-21 | User Interface: "Validation"
2018-03-30 | Extra Features | -15 | 0 | -15 | 2018-03-30 | Extra Features
2018-05-10 | Testing and Extra Feature Implementation | 12 | 0 | -30 | 2018-05-01 | User Manual (Final)
2018-05-01 | User Manual (Final) | -30 | 0 | 12 | 2018-05-10 | Testing and Extra Feature Implementation

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 20 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 36 | 17 | 1 | 2017-09-01 | Project Start | 25 | 16 | 17 | 2017-09-01 | Project Start | 25
|  |  | 16 | 2 | 2017-09-25 | Vision Document | 5 | 15 | 16 | 2017-09-25 | Vision Document | 5
|  |  | 15 | 3 | 2017-10-02 | Project Plan | -10 | 14 | 15 | 2017-10-02 | Project Plan | -10
|  |  | 14 | 4 | 2017-10-16 | Flowchart/UML | 15 | 13 | 14 | 2017-10-16 | Flowchart/UML | 15
|  |  | 13 | 5 | 2017-11-06 | Use Cases | -15 | 12 | 13 | 2017-11-06 | Use Cases | -15
|  |  | 12 | 6 | 2017-11-29 | Test Plan | 10 | 11 | 12 | 2017-11-29 | Test Plan | 10
|  |  | 11 | 7 | 2017-12-02 | User Manual Draft (Tentative) | -15 | 10 | 11 | 2017-12-02 | User Manual Draft (Tentative) | -15
|  |  | 10 | 8 | 2017-12-19 | Presentation | 15 | 9 | 10 | 2017-12-19 | Presentation | 15
|  |  | 9 | 9 | 2018-01-29 | Implementation Phase | -25 | 8 | 9 | 2018-01-29 | Implementation Phase | -25
|  |  | 7 | 10 | 2018-02-14 | Dababase Implementation | 15 | 7 | 8 | 2018-02-14 | User Interface: "Layout" | -12
|  |  | 8 | 10 | 2018-02-14 | User Interface: "Layout" | -12 | 6 | 7 | 2018-02-14 | Dababase Implementation | 15
|  |  | 4 | 13 | 2018-03-21 | User Interface: "Validation" | 25 | 5 | 6 | 2018-03-20 | Prototype Testing | -30
|  |  | 6 | 12 | 2018-03-20 | Prototype Testing | -30 | 4 | 5 | 2018-03-21 | Prototype Finished | 5
|  |  | 5 | 13 | 2018-03-21 | Prototype Finished | 5 | 3 | 4 | 2018-03-21 | User Interface: "Validation" | 25
|  |  | 3 | 15 | 2018-03-30 | Extra Features | -15 | 2 | 3 | 2018-03-30 | Extra Features | -15
|  |  | 1 | 17 | 2018-05-10 | Testing and Extra Feature Implementation | 12 | 1 | 2 | 2018-05-01 | User Manual (Final) | -30
|  |  | 2 | 16 | 2018-05-01 | User Manual (Final) | -30 | 0 | 1 | 2018-05-10 | Testing and Extra Feature Implementation | 12